## Sheet1
Project Week 5 Risk Assessment with matrix included
Risks | Risk Statement | Reponse | Objectives | Likelihood | Impact | Risk Level |  |  | Impact
Work website crashes | Unable to work | Contact tech support to rectify the issue | If server goes down have failover server | Low | High | 7 |  |  | low | medium | high
| Waste of company time and money | Have local copies saved to computer | Ensure all apps support background saving |  |  |  | Likeline of Occurrence | Low | 1 | 4 | 7
| Waste of developers time | [6 empty] | medium | 2 | 5 | 8
| May be unable to complete project on time | [6 empty] | high | 3 | 6 | 9
Data information leak | GDPR protection laws breached | Notify appropriate authorities | Setup appropriate network protection | Medium | Medium | 7
|  | contact line manager immediately | Encrypt data so it is unusable if stolen
Make full log of incident to help find fault
Fire/Building damage | Building may be inaccessble | Contact emergency services if appropriate | Insurance of property, contents and personnel | High | High | 9
| Equipment at site could be damaged | Ensure safety checks are carried out regularly | Fire prevention measures
| Risk to life |  | Continuous mainteneance of fire safety awareness
Natural disaster | Power outtage | Contact emergency services if appropriate | Insurance of property | Low | High | 8
| Servers Destroyed | Rectify issue with tech support | backups
| Building damage |  | Buildings and content unsurance
Staff illness | Could cause delays on project progress | Notify company of absence | Have a list of supply staff ready to cover when needed | High | Medium | 5
| Could risk losing job | Work overtime to get back on track
DDOS attack | Wesbite unable to operate | IP Monitoring | Setup appropriate network protection | Low | High | 7
| Potentail ransomware | Have local backups | Block malicious IPs
Unable to complete tasks
Accident At home | Risk to life | Call appropriate emergency services | Have appropriate insurances in place | High | Medium | 6
|  | Ensure first aid kit is nearby | Daily checks to building to prevent issues
Implement proper cleaning/hygiene safety rota
First Aid training for staff
Power outtage | Unable to operate | Contact power company, tech support | Have candles / backup generator ready | Low | HIgh | 7
| Unable to communicate with employer | Engage back up power supply | If server goes down have failover server
Internet Outtage | Website unable to operate | Contact ISP | Third party hosting service | Medium | Medium | 4
| Unable to access work/client servers | Attempt to resolve | Ensure background saving on all apps
Personal injury | Risk to life | Provide first aid | Maintain healthy lifestyle | Low | High | 3
| Could delay project | Seek help if necessary | Prevent risk of injury
Human Error | Staff making mistakes can cost the company | Ensure correct checks completed before submitting work. | Staff training | High | Medium | 6
Staff member could lose their job