## Sheet1
Project Week 5 Risk Assessment with matrix included
Description | Evaluation | Likelihood | Impact Level | Responsibilty | Reponse | Risk Level | Control Measures |  |  | Impact
Work website crashes | Unable to work | Low | High | Developers | Contact tech support to rectify the issue | 7 | If server goes down have failover server |  |  | low | medium | high
| Waste of company time and money |  |  |  | Have local copies saved to computer |  | Ensure all apps support background saving | Likeline of Occurrence | Low | 1 | 4 | 7
| Waste of developers time | [7 empty] | medium | 2 | 5 | 8
| May be unable to complete project on time | [7 empty] | high | 3 | 6 | 9
Data information leak | GDPR protection laws breached | Medium | Medium | Developers | Notify appropriate authorities | 7 | Setup appropriate network protection
[5 empty] | contact line manager immediately |  | Encrypt data so it is unusable if stolen
Make full log of incident to help find fault
Fire/Building damage | Building may be inaccessble | High | High | Building Owner | Contact emergency services if appropriate | 9 | Insurance of property, contents and personnel
| Equipment at site could be damaged |  |  |  | Ensure safety checks are carried out regularly |  | Fire prevention measures
| Risk to life | [5 empty] | Continuous mainteneance of fire safety awareness
Natural disaster | Power outtage | Low | High | N/A | Contact emergency services if appropriate | 8 | Insurance of property
| Servers Destroyed |  |  |  | Rectify issue with tech support |  | Have local or remote backups
| Building damage | [5 empty] | Buildings and content unsurance
Staff illness | Could cause delays on project progress | High | Medium | Staff member | Notify company of absence | 5 | Have a list of supply staff ready to cover when needed
| Could risk losing job |  |  | Company employer | Work overtime to get back on track
DDOS attack | Wesbite unable to operate | Low | High | Developers | IP Monitoring | 7 | Setup appropriate network protection
| Potentail ransomware |  |  |  | Have local backups |  | Block malicious IPs
Unable to complete tasks
Accident At home | Risk to life | High | Medium | Staff member | Call appropriate emergency services | 6 | Have appropriate insurances in place
[5 empty] | Ensure first aid kit is nearby |  | Daily checks to building to prevent issues
Implement proper cleaning/hygiene safety rota
First Aid training for staff
Power outtage | Unable to operate | Low | HIgh | Electricity supplier | Contact power company, tech support | 7 | Have candles / backup generator ready
| Unable to communicate with employer |  |  |  | Engage back up power supply |  | If server goes down have failover server
Internet Outtage | Website unable to operate | Medium | Medium | Internet Provider | Contact ISP | 4 | Third party hosting service
| Unable to access work/client servers |  |  |  | Attempt to resolve |  | Ensure background saving on all apps
Personal injury | Risk to life | Low | High | Staff member | Provide first aid | 3 | Maintain healthy lifestyle
| Could lead to long term staff absence |  |  |  | Seek help if necessary |  | Prevent risk of injury
| Could delay project |  |  |  | Ask for assistance from employer if needed
Human Error | Staff making mistakes can cost the company | High | Medium | Staff member | Ensure correct checks completed before submitting work. | 6 | Staff training
Staff member could lose their job